## Timeline 2023
|  |  |  | Deadline | OEP Secretariat Toyo University |  | UMAP IS |  | Participating Universities | Students | UMAP Japanese National Commission
1. Implementation process of OEP | [7 empty] | （UMAP member universities）
| Call for program |  |  | 2022-05-15 | Publish Application information |  | Announcement to member institutions |  | Receive
（JV Campus member universities）
Receive
Simultaneous report
| Application from participating universities |  |  | From 15-May to 23-June | Receive Application |  |  |  | Application
| Notification of results to participating universities |  |  | 2022-07-07 | Notification of results |  |  |  | Receive results
| Inform students of course information, course schedules, credits, persons in charge, and number of slots. |  |  | 2022-07-07 | release course list |  | Announcement |  | Receive information | Receive information
*Applications for up to four courses per student allowed
| Receive applications from students |  |  | From 10-Jul to 24-Jul | Receive applications |  |  |  | coordination with students | Submit application
※Studens are required to appy for the program after coordiating with home university
Matching by OEP Secretariat (Toyo University)
| Notification of matching results to students and universities providing subjects |  |  | 2022-08-04 | Notification of results |  |  |  |  | Receive results
Receive results
| Enrollment registration by students | [7 empty] | Receive registration | Enrollment registration
*The schedule on the right is an example of Toyo University.
| Notify students of the results of their registration and guide them to their courses | [7 empty] | Notification of results | Receive results
*Varies by participating universities and courses
*The schedule on the right is an example of Toyo University.
(Registration period at Toyo : 9/19 to 22)
| Report to OEP Secretariat( list of participating students from participating universities and course providers) |  |  |  | Receive reports |  |  |  | Report
Start of course
End of course
| Report from participating universities and course providers to OEP secretariat regarding the progress of participating students, issues and points for improvements related to operations. |  |  |  | Receive reports |  |  |  | Report
Report
Report